## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1317/RD/PHE | 12/05/2023 | 12/05/2023 | Resource Division | 88.18 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Estimate for the work of PMGSY Road in connection with laying of pipeline along the road shoulder. |  |  | BILL/00189/2024-2025 | BP-2024-25-127 | 22/07/2024 | 22/07/2024 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 9.21 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BAJARGAON PWSS | SM/18626 | New | Quotation for new service connection at BAJARGAON PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18626) |  |  | BILL/02085/2024-2025 | BP-2024-25-478 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 22.74 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BAJARGAON PWSS | SM/18626 | New | Quotation for new service connection at BAJARGAON PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18626) |  |  | BILL/02086/2024-2025 | BP-2024-25-479 | 09/09/2024 | 09/09/2024 | W.B.S.E.D.C.LTD | 11.71 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BAJARGAON PWSS | SM/18626 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bajargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018347) | Assistant Engineer - I | Junior Engineer-02 | ORD/000621/2023-2024 | 2730/MLMD | 14/08/2023 | 28/12/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 41.58 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Implementation of BAJARGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rd TubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000364/2023-2024 | 2480/RD/PHE | 24/08/2023 | 06/04/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 841.02 | 30.35 | 3.61 | 66
7 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Construction of Approach Road at Head Work Site, & 3rd Tube-Well Site under New Scheme of Bazargaon PWSS at Karandighi Block under Raiganj Division, PHE dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000164/2024-2025 | 2898/RD/PHE | 25/09/2024 | 25/10/2024 | SARNALI ENTERPRISE | 6.78 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BAZARGAON PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000377/2024-2025 | 3496/RD/PHE | 02/12/2024 | 16/01/2025 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 31.92 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BAJARGAON PWSS | SM/18626 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bazargaon Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000329/2025-2026 | 2014/RD/PHE | 08/07/2025 | 04/01/2026 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 36.36 | 0 | 0 | 0
Total | [13 empty] | 1089.5 | 30.35 | 2.79