## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 862/RD/PHE | 25/03/2023 | 25/03/2023 | Resource Division | 79.68 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHOMRA PWSS | SM/18627 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhomra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018346) | Assistant Engineer - I | Junior Engineer-07 | ORD/001815/2023-2024 | 3703/MLMD | 29/11/2023 | 27/05/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 37 | 0 | 0 | 78
3 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-09 under Katihar Division of Northeast Frontier Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division PHE Dte. |  |  | BILL/00098/2024-2025 | BP-2024-25-68 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER | 0.1 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division, PHE Dte. |  |  | BILL/00157/2024-2025 | BP-2024-25-105 | 09/07/2024 | 09/07/2024 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.04 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHOMRA PWSS | SM/18627 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bhomra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03632/2023-2024 | BP-2023-24-616 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 3 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHOMRA PWSS | SM/18627 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhomra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03631/2023-2024 | BP-2023-24-615 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 2.41 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj | Malda Mechanical | BHOMRA PWSS | SM/18627 | New | Additional Quotation of Bhomra TW-I in the District of Uttar Dinajpur. |  |  | BILL/01685/2024-2025 | BP-2024-25-412 | 30/07/2024 | 30/07/2024 | W.B.S.E.D.C.LTD | 1.26 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Implementation of BHOMRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000210/2023-2024 | 2293/RD/PHE | 04/08/2023 | 01/01/2026 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 890.66 | 0 | 0 | 50
9 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000225/2023-2024 | 2366/RD/PHE | 11/08/2023 | 01/02/2025 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 100
10 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhomra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000468/2024-2025 | 01/RD/PHE | 02/01/2025 | 16/02/2025 | AJIT PRAMANIK | 19.24 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Raiganj | Raiganj Division | BHOMRA PWSS | SM/18627 | New | Jack Pushing of M.S. Pipe of 300 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 23/8 to 23/9 near Jhitkia Railway Station (RGJ) for Bhomra and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. In the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000146/2024-2025 | 2833/RD/PHE | 23/09/2024 | 11/01/2025 | RAY CONSTRUCTION &CO. | 28.76 | 0 | 0 | 100
Total | [13 empty] | 1147.76 | 0 | 0