## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Implementation of BHIKHANPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000358/2023-2024 | 2474/RD/PHE | 24/08/2023 | 31/12/2025 | M/S PINKI CONSTRUCTION | 647.91 | 223.79 | 34.54 | 65
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHIKHANPUR PWSS | SM/18628 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhikhanpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018357) | Assistant Engineer - I | Junior Engineer-02 | ORD/001814/2023-2024 | 3702/MLMD | 29/11/2023 | 23/11/2026 | ANIMA ENTERPRISE | 37.03 | 29.23 | 78.93 | 88
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 829/RD/PHE | 22/03/2023 | 22/03/2023 | Resource Division | 79.15 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 642/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 78.14 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHIKHANPUR PWSS | SM/18628 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-04 | ORD/001007/2024-2025 | 4277/MLMD | 27/12/2024 | 24/02/2025 | RAMCHANDRA BASAK | 0.77 | 0.75 | 98.05 | 100
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Additional pipeline and other ancillary works at Bhikhanpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000368/2024-2025 | 3487/RD/PHE | 02/12/2024 | 16/01/2025 | RAKSHIT TRADERS | 29.04 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHIKHANPUR PWSS | SM/18628 | New | Quotation for new service connection at BHIKHANPUR PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18628) |  |  | BILL/02199/2024-2025 | BP-2024-25-520 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 13.39 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHIKHANPUR PWSS | SM/18628 | New | Quotation for new service connection at BHIKHANPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18628) |  |  | BILL/02198/2024-2025 | BP-2024-25-519 | 26/09/2024 | 26/09/2024 | W.B.S.E.D.C.LTD | 9.89 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Sheme in different Block in the District of Uttar Dinajpur under Raiganj Division,PHE Dte.. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000518/2024-2025 | 58/RD/PHE | 03/01/2025 | 12/02/2026 | TECHVISION | 5 | 0 | 0 | 83
10 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHIKHANPUR PWSS | SM/18628 | New | Restoration of damage pipeline during road widening at Bikhanpur piped water Supply Scheme at Karandighi Block Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000405/2025-2026 | 1609/RD/PHE | 17/06/2025 | 12/02/2026 | M/S PINKI CONSTRUCTION | 13.22 | 0 | 0 | 0
Total | [13 empty] | 913.52 | 253.77 | 27.78