## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 633/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 81.83 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHABANIPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000380/2024-2025 | 3499/RD/PHE | 02/12/2024 | 16/01/2025 | M/S PINKI CONSTRUCTION | 34.81 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHABANIPUR PWSS | SM/18629 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhabanipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018353) | Assistant Engineer - I | Junior Engineer-02 | ORD/000629/2023-2024 | 2733/MLMD | 14/08/2023 | 26/06/2026 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 41.69 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Implementation of BHABANIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000355/2023-2024 | 2473/RD/PHE | 24/08/2023 | 14/06/2025 | M/S PINKI CONSTRUCTION | 974.94 | 394.05 | 40.42 | 66
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Construction of concrete pathway at Head Work Site Pump House,2nd TW Site & 3rd TW Site Pump House for BHABANIPUR Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000369/2024-2025 | 3488/RD/PHE | 02/12/2024 | 01/01/2025 | SANDIP SARKAR | 9.25 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHABANIPUR PWSS | SM/18629 | New | Quotation for new service connection at BHABANIPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur (SM/18629). |  |  | BILL/02739/2024-2025 | BP-2024-25-596 | 09/01/2025 | 09/01/2025 | W.B.S.E.D.C.LTD | 8.61 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHABANIPUR PWSS | SM/18629 | New | Quotation for new service connection at BHABANIPUR PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18629) |  |  | BILL/03209/2024-2025 |  | 20/01/2025 | 20/01/2025 | W.B.S.E.D.C.LTD | 14.2 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHABANIPUR PWSS | SM/18629 | New | Quotation for new service connection at BHABANIPUR PH-II (Karandighi ccc) in the district of Uttar Dinajpur (SM/18629). |  |  | BILL/02740/2024-2025 | BP-2024-25-597 | 06/02/2025 | 06/02/2025 | W.B.S.E.D.C.LTD | 12.11 | 0 | 0 | 0
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Vehicle no.WB 59C 4762) having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office ofthe Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entireRaiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Estimator | ORD/000408/2024-2025 | 1981/RD/PHE | 29/06/2024 | 13/01/2025 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 2.6 | 0 | 0 | 100
Total | [13 empty] | 1180.03 | 394.05 | 33.39