## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 633/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 81.83 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHABANIPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000380/2024-2025 | 3499/RD/PHE | 02/12/2024 | 16/01/2025 | M/S PINKI CONSTRUCTION | 34.81 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BHABANIPUR PWSS | SM/18629 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhabanipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018353) | Assistant Engineer - I | Junior Engineer-02 | ORD/000629/2023-2024 | 2733/MLMD | 14/08/2023 | 28/12/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 41.69 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Implementation of BHABANIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000355/2023-2024 | 2473/RD/PHE | 24/08/2023 | 14/06/2025 | M/S PINKI CONSTRUCTION | 974.94 | 394.05 | 40.42 | 66
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Construction of concrete pathway at Head Work Site Pump House,2nd TW Site & 3rd TW Site Pump House for BHABANIPUR Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000369/2024-2025 | 3488/RD/PHE | 02/12/2024 | 01/01/2025 | SANDIP SARKAR | 9.25 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BHABANIPUR PWSS | SM/18629 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 10/01/2025 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
Total | [13 empty] | 1145.11 | 394.05 | 34.41