## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Chotaparua PWSS 2.Udaypur PWSS 3.Piplan PWSS 4.Barua PWSS 5.Bindol PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000327/2024-2025 | 3281/RD/PHE | 20/11/2024 | 04/01/2025 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.67 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kanki PWSS 2.Deona PWSS 3.Pokheria PWSS 4.Lodhon PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and ongoing PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000321/2024-2025 | 3277/RD/PHE | 20/11/2024 | 04/01/2025 | HAQUE CONSTRUCTION | 17.33 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Dakshin Kundalpukhur PWSS 2.Purba Chutiakhore PWSS 3.Pawakhali PWSS 4.Amalbari PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000325/2024-2025 | 3279/RD/PHE | 20/11/2024 | 04/01/2025 | M/S LUCKY CONSTRUCTION | 17.32 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Goagaon PWSS 2.Ghirnigaonkhas PWSS 3.Panjipara PWSS 4.Khowaspur PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000324/2024-2025 | 3278/RD/PHE | 20/11/2024 | 04/01/2025 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 17.34 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kasba NM PWSS 2.Sitgram PWSS 3.Sasan PWSS 4.Gutin PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000328/2024-2025 | 3282/RD/PHE | 20/11/2024 | 04/01/2025 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 17.34 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Malgaon PWSS 2.Bheur PWSS 3.Purba Rampur PWSS 4.Faridpur PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000329/2024-2025 | 3284/RD/PHE | 20/11/2024 | 04/01/2025 | UJJAL KUMAR SARKAR PARTNER | 17.33 | 0 | 0 | 0
7 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Baruna PWSS 2.Mahinagar PWSS 3.Kunore PWSS 4.Majhiar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000330/2024-2025 | 3285/RD/PHE | 20/11/2024 | 04/01/2025 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 17.33 | 0 | 0 | 0
8 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Surun PWSS 2.Shridharpur PWSS 3.Kaliganj PWSS 4.Chandol PWSS 5.Kotar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000342/2024-2025 | 3287/RD/PHE | 20/11/2024 | 04/01/2025 | PANDIT CONSTRUCTION | 21.67 | 0 | 0 | 0
9 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bamir PWSS 2.Hemtabad Zone-I PWSS 3.Poaltair PWSS 4.Tungail Bilpara PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000343/2024-2025 | 3283/RD/PHE | 20/11/2024 | 04/01/2025 | BISWADEEP MALLICK | 17.34 | 0 | 0 | 0
10 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Sergram PWSS 2.Phulatti PWSS 3.Puria PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000331/2024-2025 | 3286/RD/PHE | 20/11/2024 | 04/01/2025 | M/S BHOWMIK CONSTRUCTION | 13 | 0 | 0 | 0
11 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of Soak well at Head Work Site of Paharajpur Piped Water Supply Scheme in connection with additional source of drinking water by creating stand posts and soak gallery at different locations in each Commissioned and On-Going PWSS under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000398/2023-2024 | 2672/RD/PHE | 20/09/2023 | 20/10/2023 | M/S PRATIMA CHOUDHURY | 5.42 | 0 | 0 | 100
12 | UTTAR DINAJPUR |  | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. | SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bhutijhari PWSS 2.Matikunda PWSS 3.Goalpokhur PWSS 4.Chakulia PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, ISD | ORD/000326/2024-2025 | 3280/RD/PHE | 20/11/2024 | 03/07/2025 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 17.32 | 0 | 0 | 0
Total | [13 empty] | 200.4 | 0 | 0