## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SADIPUR PWSS | SM/18994 | New | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 640/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 46.68 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | SADIPUR PWSS | SM/18994 | New | Quotation for new service connection at SADIPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00627/2024-2025 | BP-2024-25-120 | 24/04/2024 | 24/04/2024 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | SADIPUR PWSS | SM/18994 | New | Quotation for new service connection at SADIPUR PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. |  |  | BILL/00628/2024-2025 | BP-2024-25-121 | 24/04/2024 | 24/04/2024 | W.B.S.E.D.C.LTD | 3.68 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SADIPUR PWSS | SM/18994 | New | Implementation of SADIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, ISD ,Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000421/2023-2024 | 2869/RD/PHE | 17/10/2023 | 03/07/2026 | UTTAM SAHA | 645.28 | 300.71 | 46.6 | 57
5 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | SADIPUR PWSS | SM/18994 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Sadipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018395) | Assistant Engineer - I | Junior Engineer-02 | ORD/001671/2023-2024 | 3342/MLMD | 30/10/2023 | 26/06/2026 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 25.43 | 0 | 0 | 42
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | SADIPUR PWSS | SM/18994 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sadipur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000514/2024-2025 | 3764/RD/PHED | 18/12/2024 | 01/02/2025 | M/S REGAL BUILDERS | 94.78 | 0 | 0 | 0
Total | [13 empty] | 821.27 | 300.71 | 36.61