## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BUDHRA PWSS | SM/19012 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Budhra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018370) | Assistant Engineer - I | Junior Engineer-02 | ORD/002031/2023-2024 | 4770/MLMD | 29/12/2023 | 26/06/2026 | M/S. KUNDU CONSTRACTION | 24.27 | 16.6 | 68.41 | 69
2 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Implementation of BUDHRA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer HQ,Assistant Engineer RWS SD | Junior Engineer, RSD ,Junior Engineer, RWS | ORD/000633/2023-2024 | 2888/RD/PHE | 30/10/2023 | 29/07/2025 | M/S ALISA CONSTRUCTION | 352.41 | 0 | 0 | 35
3 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 638/RD/PHE | 02/03/2023 | 02/03/2023 | Resource Division | 43.1 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000550/2023-2024 | 644/RD/PHE | 05/03/2024 | 19/04/2024 | JEET CONSTRUCTION UKILPARA | 11.29 | 0 | 0 | 0
5 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000551/2023-2024 | 645/RD/PHE | 05/03/2024 | 19/04/2024 | BITTU ENTERPRISE | 11.29 | 0 | 0 | 10
6 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 28/06/2024 | PRITAM SARKAR | 1.6 | 0.39 | 24.38 | 0
7 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BUDHRA PWSS | SM/19012 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-04 | ORD/000647/2024-2025 | 3420/MLMD | 28/10/2024 | 28/12/2024 | NITAI PANDEY | 0.78 | 0 | 0 | 100
8 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Budhra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD | Junior Engineer, RSD | ORD/000454/2024-2025 | 3767/RD/PHED | 18/12/2024 | 01/06/2025 | UTTAM SAHA | 33.94 | 0 | 0 | 60
9 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59C 0644) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 01/07/2024 to 14/01/2025. | Assistant Engineer RWS SD | Junior Engineer RWS HQ,Junior Engineer, RWS | ORD/000407/2024-2025 | 1980/RD/PHE | 29/06/2024 | 13/01/2025 | PRITAM SARKAR | 2.6 | 0.3 | 11.41 | 100
10 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BUDHRA PWSS | SM/19012 | New | Quotation for new service connection at BUDHRA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/19012). |  |  | BILL/01107/2024-2025 | BP-2024-25-256 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 7.42 | 0 | 0 | 0
11 | UTTAR DINAJPUR | Karandighi | Malda Mechanical | BUDHRA PWSS | SM/19012 | New | Quotation for new service connection at BUDHRA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/19012). |  |  | BILL/01106/2024-2025 | BP-2024-25-255 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Karandighi | Raiganj Division | BUDHRA PWSS | SM/19012 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Budhra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000335/2025-2026 | 2486/RD/PHE | 12/09/2025 | 11/03/2026 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0 | 0
Total | [13 empty] | 515.11 | 17.29 | 3.36