## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La | SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance of Laboratory of District Laboratory at Karnajora under Raiganj Division, P.H.E. Dte. For 12(twelve) Months. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000553/2022-2023 | 1009/RD/PHE | 31/03/2023 | 31/03/2024 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 13.9 | 13.9 | 100 | 100
2 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La | SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance for 01(One) Nos. Sub-District Laboratories at Goalpukhur under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000554/2022-2023 | 1010/RD/PHE | 31/03/2023 | 31/03/2024 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.36 | 8.36 | 100 | 100
3 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La | SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance for 01(One) Nos. Sub-District Laboratories at Itahar under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000555/2022-2023 | 1011/RD/PHE | 31/03/2023 | 31/03/2024 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.36 | 8.36 | 100 | 100
4 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La | SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload Data into PHED Dash Board and maintenance of Islampur Sub-District Laboratory, Islampur under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000556/2022-2023 | 1012/RD/PHE | 31/03/2023 | 31/03/2024 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.63 | 8.63 | 100 | 100
5 | UTTAR DINAJPUR |  | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La | SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload Data into PHED Dash Board and maintenance of Hemtabad Sub-District Laboratory, Hemtabad under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000557/2022-2023 | 1013/RD/PHE | 31/03/2023 | 31/03/2024 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.63 | 8.63 | 100 | 100
Total | [13 empty] | 47.87 | 47.87 | 100