## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Majlishpur and adjacent Water Supply Schemes at Goalpokhor-I Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I | Junior Engineer-02 | ORD/000199/2023-2024 | 2143/MLMD | 07/07/2023 | 03/10/2028 | SWITCHING AVO ELECTRO POWER LTD | 41.82 | 0 | 0 | 0
2 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Malgaon and adjacent Water Supply Schemes at Kaliyaganj Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I | Junior Engineer-07 | ORD/000200/2023-2024 | 2142/MLMD | 07/07/2023 | 03/10/2028 | A.K. INDUSTRIES | 41.83 | 0 | 0 | 0
3 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Khesra Water Supply Schemes at Itahar Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I | Junior Engineer-02 | ORD/000201/2023-2024 | 2141/MLMD | 07/07/2023 | 03/10/2028 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 27.84 | 0 | 0 | 0
4 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Ghrinigaon Khas and adjacent Water Supply Schemes at Chopra Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I |  | ORD/000749/2023-2024 | 2815/MLMD | 17/08/2023 | 13/11/2028 | DAS CONSTRUCTION | 20.89 | 0 | 0 | 0
5 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gunabari Water Supply Schemes at Islampur Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I |  | ORD/000761/2023-2024 | 2814/MLMD | 17/08/2023 | 13/11/2028 | AMITAVA CHAKRABORTY | 6.7 | 0 | 0 | 0
6 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gutin and adjacent Water Supply Schemes at Hemtabad Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | Assistant Engineer - I | Junior Engineer-07 | ORD/000748/2023-2024 | 2813/MLMD | 17/08/2023 | 13/11/2028 | M/S. KUNDU CONSTRACTION | 20.9 | 8.08 | 38.65 | 79
7 | UTTAR DINAJPUR |  | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division | SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Barua and adjacent Water Supply Schemes at Raiganj Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) |  |  | ORD/001832/2023-2024 | 3630/MLMD | 23/11/2023 | 19/02/2029 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 44.19 | 0 | 0 | 0
Total | [13 empty] | 204.16 | 8.08 | 3.96