## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block | SM/07078 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. [Work Order No. 1492/BD Dated 10/10/2020 & Tender No. 200 of 2020-2021] |  |  | VCH/000157/2022-2023 | BP-2022-23-26 | 16/04/2022 | 16/04/2022 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 1.82 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block | SM/07078 | Retrofitting | Acceptance cum work order for the work of Estimate for collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for different piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [PART - II (1st PHASE DPR)] |  | Junior Engineer Kushmandi | ORD/000078/2021-2022 | 924/BD | 10/05/2021 | 10/07/2021 | MOHANTA BUILDERS | 1.69 | 0 | 0 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block | SM/07078 | Retrofitting | Acceptance cum work order for the work of Withdrawn, Relaying /laying of distribution pipe line and Rising main due to Bank Protection work of river Tangon under the commandary of Dhumpara piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000015/2022-2023 | 2553/BSSD | 11/04/2022 | 06/05/2022 | SARADA ENTERPRISE | 2.18 | 0 | 0 | 1
Total | [13 empty] | 5.69 | 0 | 0