## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nunail Piped Water Supply Scheme at Balurghat Block | SM/07079 | Retrofitting | Acceptance cum Work Order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for NUNAIL PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer 1 Sub Division | ORD/000373/2021-2022 | 2935/BD | 28/12/2021 | 11/02/2022 | TARAMA CONSTRUCTION | 8.07 | 7.99 | 99.1 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nunail Piped Water Supply Scheme at Balurghat Block | SM/07079 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for NUNAIL Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1592/BD Dated :- 16/10/2020 & Tender No. 144 of 2020-2021] |  |  | VCH/000178/2022-2023 | BP-2022-23-10 | 12/04/2022 | 12/04/2022 | TARAMA CONSTRUCTION | 12.65 | 0 | 0 | 0
Total | [13 empty] | 20.71 | 7.99 | 38.59