## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Harigaon Piped Water Supply Scheme at Balurghat Block | SM/07080 | Retrofitting | Allied Work In Connection With Providing Functional House Hold Tap Connection For Harigaon PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 Sub Division | ORD/000356/2021-2022 | 548/RWS | 03/12/2021 | 02/01/2022 | GOUTAM SAHA | 4.34 | 0.25 | 5.84 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Harigaon Piped Water Supply Scheme at Balurghat Block | SM/07080 | Retrofitting | Allied Work In Connection With Providing Functional House Hold Tap Connection ForHarigaon PWSS Under Jal Swapna Programme at Balurghat Block in the District ofDakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Work Order No. 548/RWS, Dated :- 03/12/2021 & Tender No. 372 of 2021-2022) |  |  | VCH/000430/2021-2022 | 8443/3 | 02/02/2022 | 02/02/2022 | GOUTAM SAHA | 4 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Harigaon Piped Water Supply Scheme at Balurghat Block | SM/07080 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for HARIGAON Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1590/BD, Dated :- 16/10/2020 & Tender No. 103 of 2020-2021] |  |  | VCH/000402/2021-2022 | 8443/7 | 10/01/2022 | 10/01/2022 | BHOLANATH CONSTRUCTION. | 8.95 | 0 | 0 | 0
Total | [13 empty] | 17.29 | 0.25 | 1.47