## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dangram Piped Water Supply Scheme at Harirampur Block | SM/07081 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for DANGRAM Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1588/BD dt. 16/10/2020 & Tender No. 102 of 2020-2021] |  |  | VCH/000504/2021-2022 | 8443/55 | 29/03/2022 | 29/03/2022 | DIPESH BHOWMIK | 19.46 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dangram Piped Water Supply Scheme at Harirampur Block | SM/07081 | Retrofitting | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for DANGRAM Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000023/2020-2021 | 1588/BD | 16/10/2020 | 30/11/2020 | DIPESH BHOWMIK | 83.94 | 41.63 | 49.59 | 100
Total | [13 empty] | 103.4 | 41.63 | 40.26