## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Panjul Piped Water Supply Scheme at Hili Block | SM/07085 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Panjul PWSS, under Jal Swapna Programme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer Hili | ORD/000252/2021-2022 | 2197/BD | 28/09/2021 | 28/10/2021 | M/S. R.D. CONSTRUCTION | 9.08 | 0 | 0 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Panjul Piped Water Supply Scheme at Hili Block | SM/07085 | Retrofitting | Restoration of Distribution Pipeline at Agra and Kharun Mouza within Panjul Piped Water Supply Scheme at Hili Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer RWS | Junior Engineer Hili | ORD/000074/2023-2024 | 870/BD | 24/07/2023 | 23/08/2023 | SARKAR CONSTRUCTION | 4.69 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Panjul Piped Water Supply Scheme at Hili Block | SM/07085 | Retrofitting | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for PANJUL Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Hili | ORD/000025/2020-2021 | 1586/BD | 16/10/2020 | 16/12/2022 | M/S. ANWESHA ENTERPRISE | 84.95 | 47.31 | 55.68 | 1
Total | [13 empty] | 98.72 | 47.31 | 47.92