## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Goalgaon Piped Water Supply Scheme at Kushmandi Block | SM/07086 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Goalgaon PWSS Under Jal Swapna Programme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer Kushmandi | ORD/000265/2021-2022 | 2495/BD | 02/11/2021 | 12/12/2021 | R.P. CHOUDHURY CONSTRUCTION. | 4.93 | 4.76 | 96.66 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Goalgaon Piped Water Supply Scheme at Kushmandi Block | SM/07086 | Retrofitting | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for GOALGAON Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1587/BD Dated :- 16/10/2020 & Tender No. 158 of 2020-2021] |  |  | VCH/000179/2022-2023 | BP-2022-23-12 | 12/04/2022 | 12/04/2022 | CHIRANJIB DAS | 11.14 | 0 | 0 | 0
Total | [13 empty] | 16.06 | 4.76 | 29.64