## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Siala Piped Water Supply Scheme at Balurghat Block | SM/07088 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Siala PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. | Assistant Engineer RWS | Junior Engineer 1 HQ | ORD/000251/2021-2022 | 2196/BD | 28/09/2021 | 28/10/2021 | RABIN KAMETH | 6.4 | 6.39 | 99.77 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Siala Piped Water Supply Scheme at Balurghat Block | SM/07088 | Retrofitting | Formal work order for the work of Providing Functional Household Tap Connection Under Saila Pipe Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer 1 HQ,Junior Engineer 3 HQ | ORD/000055/2020-2021 | 1901/BD | 09/12/2020 | 07/02/2021 | M/S. ANWESHA ENTERPRISE | 93.45 | 154.5 | 165.33 | 1
Total | [13 empty] | 99.86 | 160.89 | 161.12