## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Baghichapur & adjoining mouzas for Bhebrahar Mouza at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000073/2020-2021 | 2039/BD | 29/12/2020 | 02/02/2021 | M/S. A.D. ENTERPRISE | 9.19 | 17.11 | 186.27 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chhatrakunda Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000058/2020-2021 | 1945/BD | 16/12/2020 | 30/01/2021 | BOSE CONSTRUCTION | 11.42 | 19.13 | 167.46 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nendra Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000043/2020-2021 | 1857/BD | 07/12/2020 | 11/01/2021 | LOKNATH ENTERPRISE | 8.61 | 9.44 | 109.63 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dolgaon Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000039/2020-2021 | 1878/BD | 07/12/2020 | 21/01/2021 | J. CHATTERJEEE & CO. | 17.71 | 27.45 | 154.98 | 1
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bahadurpur Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000064/2020-2021 | 1975/BD | 18/12/2020 | 22/01/2021 | SARKAR CONSTRUCTION | 3.54 | 6.07 | 171.21 | 1
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bahadurpur Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | VCH/000053/2021-2022 | 8443/32 | 21/06/2021 | 21/06/2021 | SARKAR CONSTRUCTION | 0.15 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for different piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [PART - IV (For On-Going PWSS)] [Work Order No. 926/BD dt. 10/05/2021 & Tender No. 52 of 2021-2022] |  |  | VCH/000490/2021-2022 | 8443/33 | 15/03/2022 | 15/03/2022 | M/S. S.D. CONSTRUCTION | 2.25 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Baghichapur Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000038/2020-2021 | 1877/BD | 07/12/2020 | 21/01/2021 | SUBODH KUMAR SAHA | 23.25 | 34.28 | 147.44 | 1
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bagichapur Piped Water Supply Scheme at Harirampur Block | SM/07089 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Muknair Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000063/2020-2021 | 1974/BD | 18/12/2020 | 22/01/2021 | KRISHNA PAUL | 3.76 | 6.9 | 183.53 | 1
Total | [13 empty] | 79.88 | 120.37 | 150.69