## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarala Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000041/2020-2021 | 1880/BD | 07/12/2020 | 21/01/2021 | NARENDRANATH PAUL | 28.29 | 22.29 | 78.78 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Deulabari Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000040/2020-2021 | 1879/BD | 07/12/2020 | 21/01/2021 | SARADA ENTERPRISE | 14.13 | 12 | 84.88 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Hansrail PWSS Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000245/2021-2022 | 1812/BSSD | 01/10/2021 | 21/10/2021 | MAYA CONSTRUCTION | 2.31 | 0 | 0 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer Balurghat,Junior Engineer Kushmandi | ORD/000076/2020-2021 | 2042/BD | 29/12/2020 | 02/02/2021 | CHHAYA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 6.89 | 5.96 | 86.54 | 100
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Piped Water Supply Scheme at Kushmandi Block | SM/07091 | Retrofitting | Acceptance cum work order for the work of Allied Work to resolve complain under PARAY SAMADHAN In Connection With Providing Functional House Hold Tap Connection For Hansrail PWSS (Deulabari Mouza and Sarala Mouza)Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer 1 Sadar | ORD/000163/2020-2021 | 230/BD | 25/01/2021 | 19/02/2021 | SARADA ENTERPRISE | 1.38 | 1.32 | 95.84 | 0
Total | [13 empty] | 53 | 41.56 | 78.43