## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer (Civil) | ORD/000047/2020-2021 | 1883/BD | 07/12/2020 | 21/01/2021 | MANAS KUMAR SAHA | 39.31 | 36.38 | 92.54 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nakarna Mouza under Makail Piped Water Based Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer (Civil) | ORD/000065/2020-2021 | 1976/BD | 18/12/2020 | 22/01/2021 | RANJAN SARKAR | 3.02 | 2.72 | 90.05 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Payment to Resource Division for Supply of Materials. (Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme) |  |  | VCH/000350/2021-2022 | BP-2021-22-78 | 11/02/2022 | 11/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, PHED. | 4.81 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Allied Work In Connection With Providing Functional House Hold Tap Connection for MAKAIL PWSS Under Jal Swapna Programme at KUSHMANDI Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer 1 Sadar | ORD/000355/2021-2022 | 546/RWS | 03/12/2021 | 02/01/2022 | MONDAL ENTERPRISE | 4.22 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Makail & adjoining mouzas for Araziminapara Mouza at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000046/2020-2021 | 1882/BD | 07/12/2020 | 11/01/2021 | M/S. R.D. CONSTRUCTION | 8.69 | 7.06 | 81.16 | 1
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Keshabpur Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000048/2020-2021 | 1884/BD | 07/12/2020 | 21/01/2021 | SARADA ENTERPRISE | 14.89 | 12.51 | 84.03 | 1
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bhikanpur Mouza under Makail Piped Water Based Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer (Civil) | ORD/000051/2020-2021 | 1887/BD | 07/12/2020 | 11/01/2021 | RAJ KUMAR KUNDU | 3.17 | 2.45 | 77.22 | 1
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2020-2021 | 1997/BD | 22/12/2020 | 22/12/2020 | Resource Division | 10.31 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mandahar Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000099/2020-2021 | 103/BD | 11/01/2021 | 15/02/2021 | EIGHTY EIGHT CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.01 | 6.66 | 83.19 | 100
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarenga Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer (Civil) | ORD/000100/2020-2021 | 104/BD | 11/01/2021 | 15/02/2021 | DIPU PRASAD. | 6.79 | 0 | 0 | 100
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme | SM/07172 | Retrofitting | Allied pipe line laying work and washout pipe line work in connection with providing Functional House Hold Tap Connection for Makail PWSS under Jal Swapna Programme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 1 Sadar | ORD/000087/2022-2023 | 305/RWS | 02/06/2022 | 27/07/2022 | RANJAN SARKAR | 1.94 | 0 | 0 | 100
Total | [13 empty] | 105.14 | 67.77 | 64.46