## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mollapara Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000067/2020-2021 | 1978/BD | 18/12/2020 | 22/01/2021 | MALAYADRI SARKAR | 4.25 | 1.62 | 37.99 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakram Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000059/2020-2021 | 1946/BD | 16/12/2020 | 30/01/2021 | BIPUL SARKAR | 21.35 | 17.56 | 82.26 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakdurga Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000052/2020-2021 | 1888/BD | 07/12/2020 | 11/01/2021 | BALURGHAT BUILDERS | 3.11 | 2.21 | 70.89 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarangbari Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000049/2020-2021 | 1885/BD | 07/12/2020 | 11/01/2021 | SUSHANTA CHOUDHURY | 0.97 | 0.78 | 80.17 | 1
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Chakramprasad and adjoining mouzas for Chakismail Mouza at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000074/2020-2021 | 2040/BD | 29/12/2020 | 02/02/2021 | R.P. CHOUDHURY CONSTRUCTION. | 6.25 | 4.96 | 79.33 | 1
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakshyam Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000075/2020-2021 | 2041/BD | 29/12/2020 | 02/02/2021 | TECHNO ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.86 | 7.91 | 80.18 | 1
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Gazipur Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000066/2020-2021 | 1977/BD | 18/12/2020 | 22/01/2021 | SUKUMAR GOSWAMI | 2.99 | 1.22 | 40.81 | 1
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprosad Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000101/2020-2021 | 105/BD | 11/01/2021 | 25/02/2021 | M/S. A.D. ENTERPRISE | 10.7 | 6 | 56.11 | 1
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprasad Piped Water Supply Scheme | SM/07173 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Mouza Gazipur, Chakramprasad & Mollapara within CHAKRAMPRASAD PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000248/2021-2022 | 1814/BSSD | 01/10/2021 | 20/12/2021 | SUKUMAR GOSWAMI | 2.5 | 0 | 0 | 1
Total | [13 empty] | 61.98 | 42.25 | 68.17