## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | Retrofitting | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000082/2021-2022 | 1061/BD | 02/06/2021 | 01/08/2021 | J.D.J. ENTERPRISE | 116.26 | 143.71 | 123.61 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | Retrofitting | Formal work order for the work of "Providing Functional Household Tap Connection Under Pundari Pipe Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte." |  | Junior Engineer Kushmandi | ORD/000176/2020-2021 | 278/BD | 01/02/2021 | 02/04/2021 | PROJECT INDIA | 90.77 | 103.86 | 114.41 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | Retrofitting | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Pundari PWSS Under Jal Swapna Programme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000093/2021-2022 | 1539/BD | 27/07/2021 | 10/09/2021 | DIPESH BHOWMIK | 31.43 | 31.42 | 99.98 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 2963/BD | 31/12/2021 | 31/12/2021 | Resource Division | 5.78 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Pundari Piped Water Supply Scheme & Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur | SM/07394 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 206/BD | 02/02/2022 | 02/02/2022 | Resource Division | 5.49 | 0 | 0 | 0
Total | [13 empty] | 249.72 | 278.99 | 111.72