## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08169 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II). |  | Junior Engineer 1 Sadar | ORD/000263/2021-2022 | 2560/BD | 09/11/2021 | 24/12/2021 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.31 | 0 | 0 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08169 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 2964/BD | 31/12/2021 | 31/12/2021 | Resource Division | 2.2 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08169 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 205/BD | 02/02/2022 | 02/02/2022 | Resource Division | 2.75 | 0 | 0 | 0
Total | [13 empty] | 46.26 | 0 | 0