## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | Retrofitting | Acceptance cum work order for the work of Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for DOMRAN & NAWAPARA and any other piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000458/2021-2022 | 2169/BSSD | 20/01/2022 | 27/01/2022 | MOHANTA BUILDERS | 1.11 | 0.66 | 59.66 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | Retrofitting | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalikamora Zone II Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer Kushmandi | ORD/000185/2020-2021 | 507/BD | 25/02/2021 | 26/04/2021 | DURJOY MITRA | 57.09 | 2.03 | 3.56 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 2965/BD | 31/12/2021 | 31/12/2021 | Resource Division | 2.2 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 203/BD | 02/02/2022 | 02/02/2022 | Resource Division | 8.24 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna programme for Kalikamora Zone - II Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur (PHASE - II) | SM/08170 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalikamora Zone II Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000272/2021-2022 | 2603/BD | 12/11/2021 | 11/01/2022 | MANAS KUMAR SAHA | 80.63 | 64.77 | 80.33 | 85
Total | [13 empty] | 149.25 | 67.46 | 45.2