## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divis | SM/09778 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil) | ORD/000322/2021-2022 | 2066/BD | 17/09/2021 | 02/10/2021 | ENVIROTECH SOLUTIONS | 2.77 | 2.77 | 100 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divis | SM/09778 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) (Work Order No. 1914/BSSD Dated - 01/12/2021 & Tender No. 408 of 2021-2022) |  |  | VCH/000214/2022-2023 | BP-2022-23-33 | 18/05/2022 | 18/05/2022 | RATAN CHANDRA SARKAR | 3.97 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divis | SM/09778 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 833/BD | 14/07/2023 | 14/07/2023 | Resource Division | 1.94 | 0 | 0 | 0
Total | [13 empty] | 8.68 | 2.77 | 31.88