## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone II at Hili Block in the District of Dakshin Dinajpur under Balurghat | SM/09780 | Augmentation | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of K.D Trimohini Piped Water Supply Scheme (Zone - II) at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000537/2021-2022 | 549/RWS | 03/12/2021 | 18/12/2021 | M/S. SOBHA & CO. | 4.31 | 0 | 0 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone II at Hili Block in the District of Dakshin Dinajpur under Balurghat | SM/09780 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1919/BSSD Dated :- 01/12/2021 & Tender No. 414 of 2021-2022] |  |  | VCH/000163/2022-2023 | BP-2022-23-21 | 16/04/2022 | 16/04/2022 | APURBA KUMAR SARKAR | 3.52 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone II at Hili Block in the District of Dakshin Dinajpur under Balurghat | SM/09780 | Augmentation | Providing Functional House Hold Tap Connection in connection with Retrofitting for K.D. Trimohini Zone-II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Hili | ORD/000252/2022-2023 | 3942/BD | 31/03/2023 | 15/05/2023 | SAPTADIP CONSTRUCTION | 50.3 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone II at Hili Block in the District of Dakshin Dinajpur under Balurghat | SM/09780 | Augmentation | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) | Assistant Engineer RWS | Junior Engineer Hili | ORD/000339/2021-2022 | 1919/BSSD | 01/12/2021 | 26/12/2021 | APURBA KUMAR SARKAR | 4.85 | 0 | 0 | 0
Total | [13 empty] | 62.97 | 0 | 0