## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone I at Hili Block in the District of Dakshin Dinajpur under Balurghat Di | SM/09781 | Augmentation | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of K.D Trimohini Piped Water Supply Scheme (Zone - I) at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000536/2021-2022 | 542/RWS | 03/12/2021 | 18/12/2021 | M/S. SOBHA & CO. | 3.54 | 0 | 0 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone I at Hili Block in the District of Dakshin Dinajpur under Balurghat Di | SM/09781 | Augmentation | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) | Assistant Engineer RWS | Junior Engineer Hili | ORD/000338/2021-2022 | 1918/BSSD | 01/12/2021 | 26/12/2021 | SARADA ENTERPRISE | 4.85 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for K.D Trimohini Piped Water Supply Scheme Zone I at Hili Block in the District of Dakshin Dinajpur under Balurghat Di | SM/09781 | Augmentation | Providing Functional House Hold Tap Connection in connection with Retrofitting for K.D. Trimohini Zone I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer Hili | ORD/000073/2023-2024 | 872/BD | 24/07/2023 | 14/07/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 27.8 | 0 | 0 | 35
Total | [13 empty] | 36.19 | 0 | 0