## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Auggumentation for Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09782 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 HQ | ORD/000307/2021-2022 | 2040/BD | 15/09/2021 | 30/09/2021 | INDRANIL DUTTA & ASSOCIATES | 2.86 | 2.83 | 98.86 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Auggumentation for Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09782 | Augmentation | Providing Functional House Hold Tap Connection in connection with Retrofitting for Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000028/2023-2024 | 371/BD | 22/05/2023 | 06/07/2023 | LOKNATH ENTERPRISE | 21.86 | 0 | 0 | 0
Total | [13 empty] | 24.72 | 2.83 | 11.45