## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09783 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | ORD/000321/2021-2022 | 2065/BD | 17/09/2021 | 02/10/2021 | ENVIROTECH SOLUTIONS | 2.92 | 2.66 | 91.08 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09783 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur (Phase - I). |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | ORD/000083/2022-2023 | 1248/BD | 14/06/2022 | 14/07/2022 | R.K. CONSTRUCTION | 9.02 | 8.24 | 91.28 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09783 | Augmentation | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) | Assistant Engineer RWS | Junior Engineer 1 Sadar | ORD/000330/2021-2022 | 1913/BSSD | 01/12/2021 | 26/12/2021 | RANJAN SARKAR | 4.83 | 4.73 | 97.94 | 100
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Divisi | SM/09783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 831/BD | 11/05/2022 |  | Resource Division | 1.66 | 0 | 0 | 0
Total | [13 empty] | 18.43 | 15.62 | 84.79