## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P. | SM/09784 | Augmentation | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000341/2021-2022 | 1921/BSSD | 01/12/2021 | 26/12/2021 | SREEMAA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.78 | 3.32 | 69.52 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part)Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P. | SM/09784 | Augmentation | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000538/2021-2022 | 550/RWS | 03/12/2021 | 18/12/2021 | ENVIROTECH SOLUTIONS | 3.4 | 2.99 | 87.99 | 1
Total | [13 empty] | 8.18 | 6.31 | 77.2