## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09785 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Balurghat | ORD/000320/2021-2022 | 2064/BD | 17/09/2021 | 02/10/2021 | ENVIROTECH SOLUTIONS | 2.82 | 2.28 | 80.8 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09785 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1920/BSSD Dated :- 01/12/2021 & Tender No. 375 of 2021-2022] |  |  | VCH/000161/2022-2023 | BP-2022-23-24 | 16/04/2022 | 16/04/2022 | MAYA CONSTRUCTION | 4.18 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09785 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 832/BD | 11/05/2022 | 11/05/2022 | Resource Division | 3.36 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Divisio | SM/09785 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase-II). | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000167/2022-2023 | 4005/BD | 09/01/2023 | 10/03/2023 | M/S. SARKAR ENTERPRISE | 52.66 | 0 | 0 | 0
Total | [13 empty] | 63.02 | 2.28 | 3.62