## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09786 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000319/2021-2022 | 2050/BD | 15/09/2021 | 30/09/2021 | ENVIROTECH SOLUTIONS | 2.7 | 2.19 | 81.09 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09786 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur (Phase - I) |  | Junior Engineer 2 | ORD/000032/2022-2023 | 845/BD | 12/05/2022 | 11/06/2022 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 10.27 | 8.97 | 87.34 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09786 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1917/BSSD Dated :- 01/12/2021 & Tender No. 415 of 2021-2022] |  |  | VCH/000164/2022-2023 | BP-2022-23-19 | 16/04/2022 | 16/04/2022 | DIPU PRASAD. | 4.86 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection (part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09786 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 834/BD | 11/05/2022 | 11/05/2022 | Resource Division | 1.3 | 0 | 0 | 0
Total | [13 empty] | 19.13 | 11.15 | 58.32