## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Banshihari Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001226/2021-2022 | 546 /MLMD | 28/03/2022 | 27/04/2022 | MANIK CHANDRA SAHA | 6.04 | 5.55 | 91.91 | 1
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Banshihari Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001227/2021-2022 | 547 /MLMD | 28/03/2022 | 27/04/2022 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 6.03 | 5.43 | 89.9 | 1
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Bansihari piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001266/2021-2022 | 476 /MLMD | 24/03/2022 | 23/04/2022 | JOYSHREE CONCERN | 2.74 | 2.73 | 99.47 | 1
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Banshihari piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001268/2021-2022 | 477 /MLMD | 24/03/2022 | 23/04/2022 | JOY MAA SANTOSHI ENTERPRISE | 2.74 | 2.71 | 98.85 | 1
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Formal work order for the work of Laying distribution pipe line for Augmentation of Bansihari piped water supply scheme at Bansihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000420/2021-2022 | 74/BD | 11/01/2022 | 11/04/2022 | NEOGI ENTERPRISE | 150.48 | 141.09 | 93.76 | 98
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur (Phase - II). | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 3 | ORD/000033/2022-2023 | 854/BD | 12/05/2022 | 26/06/2022 | USHA ENTERPRISE | 43.26 | 35.19 | 81.34 | 98
7 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Claim for purchase of fuel for different site visit under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II |  | ORD/001611/2021-2022 | 1808/ MLMD | 26/10/2021 | 26/04/2022 | SHAKTI FILLING STATION | 0.91 | 0.91 | 100 | 0
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Acceptance cum Work Order for Laying of HDPE pipe for water supply system by trenchless method using Horizontal Direct Drilling (HDD) method at different road crossing and congested areas on PWD road from Mollapara to Mahugram brick field under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block under Balurghat Division, PHE Dte in the district of Dakshin Dinajpur. |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000128/2022-2023 | 1774/HQ/BD | 30/08/2022 | 14/09/2022 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.81 | 4.81 | 100 | 1
9 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | claim for purchase of fuel for different site visigiet under Malda Mechanical Division, P.H.E. Dte., | Assistant Engineer - II |  | ORD/001486/2021-2022 | 1808/MLMD | 26/10/2021 | 21/12/2021 | SHAKTI FILLING STATION | 1.77 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2021-2022 | 343/BD | 22/02/2022 | 22/02/2022 | Resource Division | 1.6 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 836/BD | 11/05/2022 | 11/05/2022 | Resource Division | 6.87 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Repairing and Renovation of 2nd TW site Pump house at Banshihari PWSS of Banshihari Block under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000191/2022-2023 | 3515/BD | 04/03/2023 | 24/03/2023 | MOTAHAR HOSSAIN | 2.67 | 2.19 | 82.02 | 100
13 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Repairing and Renovation of Head Work site Pump house at Banshihari PWSS of Banshihari Block under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 1 Sadar | ORD/000253/2022-2023 | 3947/BD | 31/03/2023 | 20/04/2023 | BHASKAR BHOWMIK | 2.58 | 1.85 | 71.81 | 100
14 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/001544/2023-2024 | 1145/MLMD | 26/06/2023 | 26/12/2023 | RAMCHANDRA BASAK | 0.86 | 0.86 | 100 | 100
15 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 2314/BD | 22/11/2024 | 22/11/2024 | Resource Division | 7.69 | 0 | 0 | 0
16 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Bansihari Piped Water Supply Scheme at Bansihari Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09797 | Augmentation | Construction of 350 Cum Capacity OHR with 20mtr. Staging height, including with Soil Investigation for Augmentation of Banshihari piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. in the district of Dakshin Dinajpur. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000224/2022-2023 | 3816/BD | 23/03/2023 | 18/12/2023 | MATIUR RAHAMAN | 144.62 | 68.34 | 47.26 | 85
Total | [13 empty] | 385.67 | 271.65 | 70.44