## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Saidpur Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001400/2021-2022 | 551/MLMD | 28/03/2022 | 27/04/2022 | DAS CONSTRUCTION | 6.04 | 5.43 | 89.89 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Acceptance cum work order for the work of Laying of distribution pipe line for Augmentation of Saidpur piped water supply scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000415/2021-2022 | 75/BD | 11/01/2022 | 12/03/2022 | ASHIT KUMAR DEBSHARMA | 79.45 | 79.25 | 99.75 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur (Phase - II). |  | Junior Engineer Kushmandi | ORD/000031/2022-2023 | 844/BD | 12/05/2022 | 26/06/2022 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 34.57 | 34.08 | 98.59 | 1
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Acceptance cum Work Order for Allied work for Laying Distribution pipe line for Saidpur P.W.S.S. at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000079/2022-2023 | 2627/BSSD | 26/05/2022 | 10/06/2022 | ASHIT KUMAR DEBSHARMA | 2.32 | 2.3 | 99.37 | 1
5 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Saidpur piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001398/2021-2022 | 475/MLMD | 24/03/2022 | 03/04/2022 | J.K ENGINEERING CO. | 2.75 | 2.73 | 99.35 | 1
6 | DAKSHIN DINAJPUR |  | Central Drilling | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | ADDITIONAL TRANSPORTATION OF WASHED GRAVELS BEYOND 200 KM FOR SAIDPUR W/S SCH REPLACEMENT TUBE WELL UNDER CDD, PHE DTE. |  |  | ORD/000311/2022-2023 | 582/CMSD-I | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.79 | 0.38 | 48.5 | 1
7 | DAKSHIN DINAJPUR |  | Central Drilling | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILIZING MACHINERIES FOR SAIDPUR W/S SCH (REPLACEMENT TW), UNDER DAKSHIN DINAJPUR DISTRICT, UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000317/2022-2023 | 1167/CDD | 09/11/2022 | 09/12/2022 | C.M. ENTERPRISE | 8.55 | 6.07 | 70.94 | 1
8 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Saidpur, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000785/2023-2024 | 4003209047 | 10/08/2023 | 08/11/2023 | W.B.S.E.D.C.LTD | 0.44 | 0.44 | 100 | 100
9 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Saidpur, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000784/2023-2024 | 4003209051 | 10/08/2023 | 08/11/2023 | W.B.S.E.D.C.LTD | 0.4 | 0.4 | 100 | 100
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2021-2022 | 344/BD | 22/02/2022 | 22/02/2022 | Resource Division | 0.57 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 839/BD | 11/05/2022 | 11/05/2022 | Resource Division | 4.69 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 127/BD | 18/04/2023 | 18/04/2023 | Resource Division | 5.62 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Saidpur Piped Water Supply Scheme at Harirampur Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09805 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SAYEDPUR Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000962/2022-2023 | 2948/MLMD | 28/12/2022 | 21/10/2024 | MANIK CHANDRA SAHA. | 10.47 | 9.22 | 88.02 | 100
Total | [13 empty] | 156.66 | 140.3 | 89.56