## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Kumarganj Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001225/2021-2022 | 545 /MLMD | 28/03/2022 | 27/04/2022 | M/S. KUNDU CONSTRACTION | 6.19 | 5.58 | 90.11 | 1
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KUMARGANJ Water Supply Scheme T/W no.I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000961/2022-2023 | 2947/MLMD | 28/12/2022 | 26/02/2023 | DEVI ENTERPRISE... | 10.72 | 9.09 | 84.87 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Formal work order for the work of Laying distribution pipe line for Augmentation of Kumarganj piped water supply scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000418/2021-2022 | 73/BD | 11/01/2022 | 04/01/2025 | PRADIP KUMAR PAUL | 179.77 | 170.29 | 94.73 | 96
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2021-2022 | 345/BD | 22/02/2022 | 22/02/2022 | Resource Division | 8.08 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 838/BD | 11/05/2022 | 11/05/2022 | Resource Division | 10.77 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Laying of Rising Main, Construction of 400 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House (H/W site & 2nd TW site) and construction of Boundary Wall for Augmentation of KUMARGANJ Piped Water Supply Scheme at Kumaragnj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Kumarganj | ORD/000077/2023-2024 | 887/BD | 24/07/2023 | 01/05/2026 | MOHANTA BUILDERS | 148.99 | 17.09 | 11.47 | 25
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur (Phase - II). | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000166/2022-2023 | 2933/BD | 11/01/2023 | 27/08/2025 | KAMIRUL SK AND CO. | 77.7 | 71.5 | 92.02 | 56
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at different locations of Kumarganj and Agachha Piped Water Supply Scheme under Kumarganj Block , Balurghat Division, PHE Dte in the District of Dakshin Dinajpur. | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000145/2023-2024 | 1429/BD | 08/09/2023 | 08/10/2023 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 9.69 | 4.8 | 49.53 | 100
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 574/BD | 19/06/2023 | 19/06/2023 | Resource Division | 3.34 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 144/BD | 24/04/2023 | 24/04/2023 | Resource Division | 16.05 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Supply, Installation & Commissioning of electro-mechanical components at T/W No-I of Kumarganj W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. |  | Junior Engineer-01 | ORD/002627/2023-2024 | 1050/MLMD | 15/03/2024 | 29/03/2024 | D.R. ENTERPRISE. | 1.7 | 1.7 | 100 | 100
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer 1 HQ | ORD/000132/2024-2025 | 2095/BD | 22/10/2024 | 11/11/2024 | BIPUL SARKAR | 5.17 | 4.85 | 93.81 | 100
13 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Kumarganj Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09806 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 2319/BD | 22/11/2024 | 22/11/2024 | Resource Division | 12.06 | 0 | 0 | 0
Total | [13 empty] | 490.21 | 284.9 | 58.12