## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Chakvrigu piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001243/2021-2022 | 480 /MLMD | 24/03/2022 | 23/04/2022 | SUDIP DEY | 3.1 | 3.09 | 99.52 | 1
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Chakvrigu piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001263/2021-2022 | 481 /MLMD | 24/03/2022 | 23/04/2022 | DEVI ENTERPRISE... | 3.11 | 3.09 | 99.63 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 347/BD | 22/02/2022 | 22/02/2022 | Resource Division | 2.01 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 837/BD | 11/05/2022 | 11/05/2022 | Resource Division | 7.22 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 08/BD | 04/04/2023 | 04/04/2023 | Resource Division | 10.38 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Chakvrigu Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001229/2021-2022 | 549 /MLMD | 28/03/2022 | 27/04/2022 | SUBRATA KUMAR DAS. | 6.17 | 5.57 | 90.33 | 100
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Special Repairing and Overhauling of Existing Filter Media for the 02 nos vessel as well as change of MNO2 for Oxidation Chamber i.c.w. better running of IEP in all respect at Chakvrigu Piped Water Supply Scheme in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Balurghat | ORD/000175/2023-2024 | 1878/BD | 22/11/2023 | 22/12/2023 | ZEOLITE FRESH INDIA | 11.86 | 8.81 | 74.27 | 97
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Laying of Rising Main, Repairing of existing 600 Cum capacity OHR with 20m Staging Height, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Chak Bhrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Balurghat | ORD/000225/2022-2023 | 3828/BD | 24/03/2023 | 23/05/2023 | M/S. S. CONSTRUCTION | 33.85 | 23.54 | 69.54 | 45
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Laying of balance Distribution of pipeline and allied works for Augmentation of Chakbhrigu Piped Water Supply Scheme (Block-Balurghat) under Balurghat Division, PHE Dte in the District of Dakshin Dinajpur. |  |  | ORD/000044/2025-2026 | 8001/BD | 12/06/2025 | 10/09/2025 | MOHANTA BUILDERS | 170.25 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Formal work order for the work of Laying of distribution system for the proposed Augmentation of Chak Bhrigu water supply scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (2nd Call) | Assistant Engineer RWS | Junior Engineer HQ 2 | ORD/000511/2021-2022 | 227/BD | 08/02/2022 | 09/05/2022 | BHOLANATH CONSTRUCTION. | 143.42 | 0 | 0 | 20
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase-II). | Assistant Engineer RWS | Junior Engineer 2 HQ | ORD/000167/2022-2023 | 4005/BD | 09/01/2023 | 10/03/2023 | M/S. SARKAR ENTERPRISE | 52.66 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H.E. Dte. | SM/09833 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Chakvrigu Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001228/2021-2022 | 548 /MLMD | 28/03/2022 | 16/09/2024 | MERCURY ENGINEERING COMPANY | 6.24 | 5.58 | 89.33 | 60
Total | [13 empty] | 450.26 | 49.68 | 11.03