## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Agacha Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001230/2021-2022 | 550 /MLMD | 28/03/2022 | 27/04/2022 | PABITRA MANDAL | 6.19 | 5.7 | 92.11 | 1
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Agacha piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001254/2021-2022 | 479 /MLMD | 24/03/2022 | 23/04/2022 | M/S D.G.B. ENTERPRISE | 3.1 | 3.09 | 99.65 | 1
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Agachha piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/001260/2021-2022 | 478 /MLMD | 24/03/2022 | 23/04/2022 | HANNAN BUILDERS PVT. LTD. | 3.1 | 3.09 | 99.54 | 1
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Making compound lighting arrangement with allied works at T/W no. I of Agachha Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009294) | Assistant Engineer - I | Junior Engineer-01 | ORD/000603/2023-2024 | 2649/MLMD | 10/08/2023 | 24/09/2023 | M/S. MAYUKH BHADURI | 2.27 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of AGACHA Water Supply Scheme T/W no.II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I |  | ORD/000726/2022-2023 | 2272/MLMD | 31/08/2022 | 15/10/2022 | KARMAKAR CONSTRICTION | 7.37 | 7.37 | 100 | 100
6 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-04 | ORD/000085/2023-2024 | 645/MLMD | 06/04/2023 | 06/06/2023 | RAMCHANDRA BASAK | 0.29 | 0.28 | 99.69 | 100
7 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-I ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000447/2023-2024 | 645/MLMD. | 06/04/2023 | 05/06/2023 | RAMCHANDRA BASAK | 0.51 | 0.51 | 100 | 100
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2021-2022 | 346/BD | 22/02/2022 | 22/02/2022 | Resource Division | 1.65 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 835/BD | 11/05/2022 | 11/05/2022 | Resource Division | 8.88 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 145/BD | 24/04/2023 | 24/04/2023 | Resource Division | 31.59 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at different locations of Kumarganj and Agachha Piped Water Supply Scheme under Kumarganj Block , Balurghat Division, PHE Dte in the District of Dakshin Dinajpur. | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000145/2023-2024 | 1429/BD | 08/09/2023 | 08/10/2023 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 9.69 | 4.8 | 49.53 | 100
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 2318/BD | 22/11/2024 | 22/11/2024 | Resource Division | 9.95 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Shifting & diversion of 11KV HTOH line from the PHE site at Agacha, PS-Kumarganj |  |  | BILL/02478/2024-2025 | BP-2024-25-572 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.LTD | 4.24 | 0 | 0 | 0
14 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur (Phase - II) | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000043/2022-2023 | 919/BD | 26/05/2022 | 26/05/2025 | NARENDRANATH PAUL | 67.68 | 58.11 | 85.87 | 90
15 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Agachha Piped Water Supply Scheme in Kumarganj Block of Dakshin Dinajpur District. | SM/09834 | Augmentation | Laying of Rising Main, Construction of 350 cum capacity OHR with 20m Staging Height Including with Soil Investigation, Repairing of Pump House (H/W site & 2nd TW site), Blower Room, repairing of Boundary Wall for Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000097/2023-2024 | 1095/BD | 10/08/2023 | 02/10/2025 | BOSE CONSTRUCTION | 170.22 | 0 | 0 | 18
Total | [13 empty] | 326.72 | 82.95 | 25.39