## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection(part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09889 | Augmentation | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Agaccha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kumarganj | ORD/000311/2021-2022 | 2046/BD | 15/09/2021 | 30/09/2021 | M/S. SOBHA & CO. | 2.83 | 2.83 | 99.97 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection(part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09889 | Augmentation | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Agacha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1915/BSSD dt. 01/12/2021 & Tender No. 378 of 2021-2022] |  |  | VCH/000568/2021-2022 | BP-2021-22-147 | 25/03/2022 | 25/03/2022 | R.P. CHOUDHURY CONSTRUCTION. | 4.27 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection(part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09889 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 830/BD | 11/05/2022 | 11/05/2022 | Resource Division | 2.46 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection(part) Under Jal Swapna Programme and Prepartion of DPR in connection with Augmentation for Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division | SM/09889 | Augmentation | Providing Functional House Hold Tap connection under Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of DakshinDinajpur (Phase - I) | Assistant Engineer RWS | Junior Engineer Kumarganj | ORD/000042/2022-2023 | 918/BD | 26/05/2022 | 05/05/2024 | MAA CHANCHALA CONSTRUCTION | 22.55 | 20.21 | 89.61 | 1
Total | [13 empty] | 32.11 | 23.04 | 71.76