## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional House Hold Tap Connection by retrofitting of Zone-IX of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000539/2021-2022 | 438/BD | 14/03/2022 | 13/05/2022 | M/S. N. ISLAM AND CO. | 57.84 | 57.45 | 99.32 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Supply of different dia. Sluice Valve for piped water supply scheme for Zone-IV (Phase-I) of Gangarampur Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block, in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. [Work Order No. 114/RWS Dated :- 28/02/2022 & Tender No. 526 of 2021-2022] |  |  | VCH/000159/2022-2023 | BP-2022-23-25 | 16/04/2022 | 16/04/2022 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.73 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-II of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) [Work Order No. 133/BD Dated :- 25/01/2022 & Tender No. 432 of 2021-2022] |  |  | VCH/000173/2022-2023 | BP-2022-23-3 | 12/04/2022 | 12/04/2022 | MOHANTA BUILDERS | 84.34 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for Gangarampur Sub-Surface piped water supply scheme western sector in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) [Work Order No. 116/RWS Dated :- 28/02/2022 & Tender No. 517 of 2021-2022] |  |  | VCH/000160/2022-2023 | BP-2022-23-17 | 16/04/2022 | 16/04/2022 | MOHANTA BUILDERS | 2.22 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-III of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I). [Work Order No. 134/BD Dated :- 25/01/2022 & Tender No. 459 of 2021-2022] |  |  | VCH/000158/2022-2023 | BP-2022-23-15 | 16/04/2022 | 16/04/2022 | ASHOK MITRA | 50.12 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Formal work order for the work of Providing Functional household Tap connection by retrofitting at ZONE-III of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I). |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000463/2021-2022 | 134/BD | 25/01/2022 | 25/04/2022 | ASHOK MITRA | 161.08 | 30.22 | 18.76 | 93
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional House Hold Tap Connection by retrofitting of Zone-VIII of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000006/2022-2023 | 1249/BD | 14/06/2022 | 13/08/2022 | M/S. N. ISLAM AND CO. | 54.27 | 54.15 | 99.78 | 1
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional Household Tap connection by retrofitting at ZONE-IV of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. (PHASE-I). |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000037/2022-2023 | 912/BD | 25/05/2022 | 23/08/2022 | DURJOY MITRA | 119.41 | 72.99 | 61.13 | 70
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional House Hold Tap Connection by retrofitting of Zone-X of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). | Assistant Engineer Sadar | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000149/2022-2023 | 3520/BD | 04/03/2023 | 03/05/2023 | M/S. ANWESHA ENTERPRISE | 76.03 | 24.08 | 31.67 | 35
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Erection of Support Structure by driving Bullah piles for Khari Crossing at Sukdevpur, Maharajpur, Thengapara, Pargaon, Joypur, Karial, Nildanga Mouza under Zone-II, III & IV of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000184/2022-2023 | 3344/BD | 17/02/2023 | 19/03/2023 | SATELLITE CONSTRUCTION | 31.34 | 10.87 | 34.68 | 40
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-XII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte.(PHASE-I) | Assistant Engineer Sadar | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000168/2022-2023 | 3966/BD | 31/03/2023 | 29/06/2023 | DURJOY MITRA | 98.11 | 77.91 | 79.41 | 82
12 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-XIII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) | Assistant Engineer Sadar | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000170/2022-2023 | 3965/BD | 31/03/2023 | 29/06/2023 | M/S. TRILOCHAN CONSTRUCTION CO. | 96.19 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying of balance portion of distribution pipe line at Jalilpur Mouza to connect with the existing pipeline under Zone-V of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000200/2022-2023 | 3511/BD | 04/03/2023 | 24/03/2023 | ANIMA CONSTRUCTION | 1.71 | 1.7 | 99.51 | 0
14 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-VI of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000005/2023-2024 | 42/BD | 08/04/2023 | 07/07/2023 | AJIT PRAMANICK | 208.5 | 0 | 0 | 0
15 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-V of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte.(PHASE-I) |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000535/2021-2022 | 428/BD | 10/03/2022 | 08/06/2022 | DIPESH BHOWMIK | 120.42 | 84.45 | 70.13 | 1
16 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Headwork Site compound for Zone - V under Gangarampur Western Sector of Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000106/2023-2024 | 1333/BD | 25/08/2023 | 24/09/2023 | RANJAN CONSTRUCTION | 5.42 | 0 | 0 | 0
17 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying of HDPE pipeline in Various Zone under Gangarampur Sub Surface Based Piped Water Supply Scheme by using Horizontal Direct Drilling (HDD) method at Gangarampur Block, in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000185/2022-2023 | 3345/BD | 17/02/2023 | 19/03/2023 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 25.42 | 22.71 | 89.35 | 100
18 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Extension of overflow and washout pipeline at Zone I, Zone V Gangarampur OHR of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000190/2022-2023 | 3517/BD | 04/03/2023 | 24/03/2023 | MOTAHAR HOSSAIN | 3.24 | 3.24 | 100 | 100
19 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying pipe line for drainage of excess water from GLR site of Gangarampur Sub Surface Based Piped Water Supply Scheme of Eastern Sector at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000227/2022-2023 | 3836/BD | 24/03/2023 | 23/04/2023 | GOUTAM SAHA | 6.69 | 6.2 | 92.69 | 100
20 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 140/BD | 27/01/2022 | 27/01/2022 | Resource Division | 5.97 | 0 | 0 | 0
21 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 166/BD | 31/01/2022 | 31/01/2022 | Resource Division | 22.51 | 0 | 0 | 0
22 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 202/BD | 02/02/2022 | 02/02/2022 | Resource Division | 21.96 | 0 | 0 | 0
23 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2133/BD | 21/09/2022 | 21/09/2022 | Resource Division | 86.24 | 0 | 0 | 0
24 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 100/BD | 13/04/2023 | 13/04/2023 | Resource Division | 14.92 | 0 | 0 | 0
25 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 105/BD | 17/04/2023 | 17/04/2023 | Resource Division | 12.36 | 0 | 0 | 0
26 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Collection of Functional House Hold Tap Connection details in prescribed format under JJM Programme including uploading in IMIS portal for Gangarampur Sub Surface piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase ¿ III) | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000180/2023-2024 | 1958/BD | 08/12/2023 | 07/01/2024 | SHYAMAL CHANDRA MANDAL | 3.46 | 2.47 | 71.4 | 75
27 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional House Hold Tap Connection by retrofitting of Zone-XI of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte |  |  | ORD/000164/2024-2025 | 2231/BD | 12/11/2024 | 11/01/2025 | MATIUR RAHAMAN | 49.4 | 0 | 0 | 0
28 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000394/2021-2022 | 595/RWS | 31/12/2021 | 30/01/2022 | GOUTAM SAHA | 4.6 | 3.7 | 80.41 | 0
29 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection work at ZONE-X of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000001/2022-2023 | 533/BD | 04/04/2022 | 03/07/2022 | ASHIT KUMAR DEBSHARMA | 106.13 | 35.83 | 33.76 | 100
30 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for Gangarampur Sub Surface piped water supply scheme eastern sector in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000086/2022-2023 | 304/RWS | 02/06/2022 | 02/07/2022 | MOHANTA CONSTRUCTION | 4.66 | 4.66 | 100 | 100
31 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - IV under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000086/2023-2024 | 916/BD | 26/07/2023 | 25/08/2023 | RABIN KAMETH | 4.4 | 4.38 | 99.54 | 100
32 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - III under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000080/2023-2024 | 894/BD | 25/07/2023 | 24/08/2023 | M/S. PRASANNA CONSTRUCTION | 4.62 | 4.51 | 97.61 | 100
33 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Erection of Support Structure and allied work adjacent to Patan Bridge at Narayanpur under Zone - II & III of Gangarampur Sub-surface based Piped Water supply Scheme under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000199/2023-2024 | 275/BD | 23/02/2024 | 24/03/2024 | SUSHANTA SAHA | 18.04 | 4.73 | 26.19 | 100
34 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Urgent restoration of shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Sitahar Behera Pukur Road from chainage 5.4 Km to 7.20 km |  |  | BILL/00209/2024-2025 | BP-2024-25-132 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 10.31 | 0 | 0 | 0
35 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional House Hold Tap Connection by retrofitting of Zone-XIV of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). | Assistant Engineer Sadar | Junior Engineer 1 Sadar | ORD/000009/2022-2023 | 2868/BD | 05/01/2023 | 03/02/2025 | M/S. NANDY ENTERPRISE | 54.66 | 28.64 | 52.4 | 90
36 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Providing Functional household Tap connection by retrofitting at ZONE-VII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (PHASE-I) | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000002/2023-2024 | 43/BD | 08/04/2023 | 02/04/2025 | M/S. MAA TARA CONSTRUCTION | 98.85 | 67.27 | 68.05 | 98
37 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying of additional Distribution Pipe Line for providing balance FHTC at ZONE IX of Gangarampur Sub Surface based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000174/2024-2025 | 2073/BD | 20/11/2024 | 09/04/2025 | MINATI CONSTRUCTION | 25.75 | 0 | 0 | 30
38 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying of additional Distribution Pipe Line for providing balance FHTC at ZONE X of Gangarampur Sub Surface based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000173/2024-2025 | 2267/BD | 20/11/2024 | 04/04/2025 | MAA CHANCHALA CONSTRUCTION | 24.42 | 0 | 0 | 75
39 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone ¿ I under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer 1 Sadar,Junior Engineer 2 | ORD/000085/2023-2024 | 904/BD | 25/07/2023 | 24/08/2023 | POPY ENTERPRISE | 4.12 | 4.11 | 99.88 | 90
40 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting of existing OHR and other allied structures at Zone - II (600 CUM) of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer Kushmandi | ORD/000075/2023-2024 | 875/BD | 24/07/2023 | 23/08/2023 | SARKAR CONSTRUCTION | 5.16 | 0 | 0 | 100
41 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Laying of distribution pipeline at Ramchandrapur Mouza for Gap closing near Railway Crossing of Zone-VI under Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000187/2023-2024 | 2043/BD | 14/12/2023 | 13/01/2024 | A.B. ENTERPRISE | 9.92 | 9.92 | 99.99 | 100
42 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - XI under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000127/2024-2025 | 1909/BD | 26/09/2024 | 22/11/2024 | POPY ENTERPRISE | 6.88 | 0 | 0 | 100
43 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - IX under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000142/2024-2025 | 1970/BD | 27/09/2024 | 25/01/2025 | RANJIT BARMAN | 6.04 | 0 | 0 | 100
44 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - X under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000130/2024-2025 | 1905/BD | 26/09/2024 | 26/10/2024 | RABIN KAMETH | 5.96 | 5.88 | 98.7 | 100
45 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - VI under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000158/2024-2025 | 2215/BD | 05/11/2024 | 05/12/2024 | MAA TARA ENTERPRISE | 4.11 | 0 | 0 | 100
46 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Construction of Approach road, and other allied works of Head Works Site compound for Zone - XII under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000143/2024-2025 | 1993/BD | 30/09/2024 | 30/10/2024 | M/S. SAHA CONSTRUCTION | 2.86 | 0 | 0 | 100
47 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Gangarampur & Harirampur Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000125/2024-2025 | 1914/BD | 26/09/2024 | 16/10/2024 | ASHIT KUMAR DEBSHARMA | 8.35 | 0 | 0 | 100
48 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - VII under Gangarampur Eastern Sector of Gangarampur Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000126/2024-2025 | 1915/BD | 26/09/2024 | 28/02/2025 | M/S. PRASANNA CONSTRUCTION | 7.17 | 0 | 0 | 100
49 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - VIII under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000128/2024-2025 | 1908/BD | 26/09/2024 | 26/10/2024 | M/S. BANI CONSTRUCTIUON | 6.81 | 0 | 0 | 100
50 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - XIV under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000129/2024-2025 | 1907/BD | 26/09/2024 | 26/10/2024 | HENA CONSTRUCTION | 6.48 | 6.44 | 99.26 | 100
51 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of 13 nos Zones under Gangarampur Sub Surface Based Piped Water Supply Project in the District of Dakshin Dinajpur (Phase I) | SM/10024 | Retrofitting | Face lifting related works of Head Works Site compound for Zone - XIII under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000141/2024-2025 | 1969/BD | 27/09/2024 | 27/10/2024 | M/S. MAA TARA CONSTRUCTION | 5.37 | 0 | 0 | 100
Total | [13 empty] | 1858.53 | 628.48 | 33.82