## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | Consultancy Service for Preparation of Revised drawing of Distribution network followed by detail Survey and design of pipe line for Ellahbad Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.E. Dte. | Assistant Engineer HQ | Junior Engineer (Civil) | ORD/000373/2022-2023 | 896/BD | 23/05/2022 | 22/06/2022 | M/S SOBHA & CO. | 2.47 | 2.31 | 93.69 | 100
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | SUPPLY,DELIVERY,INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY AND OTHER ALLIED ACCESSORIES AT ELAHABAD WATER SUPPLY SCHEME IN THE DISTRICT OF DAKSHIN DINAJPUR UNDER MALDA MECHANICAL DIVISION, PHED. | Assistant Engineer - I | Junior Engineer-01 | ORD/001783/2023-2024 | 3453/MLMD | 03/11/2023 | 01/05/2024 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 11.54 | 11 | 95.3 | 96
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of Pump House for implementation of Piped Water Supply Scheme for Elahabad Mouza in connection with parent Scheme of Pond Based Piped Water Supply Scheme Using Nandan Bill Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer (Civil) | ORD/000204/2022-2023 | 3508/BD | 04/03/2023 | 27/02/2025 | NILKAMAL BASAK | 219.05 | 190.54 | 86.98 | 78
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Elahabad W/S Sch Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001873/2023-2024 | 4003270120 | 17/11/2023 | 15/02/2024 | W.B.S.E.D.C.LTD | 11.54 | 11.54 | 100 | 100
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 3538/BD | 10/03/2023 | 10/03/2023 | Resource Division | 38.09 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Revised Detailed Project Report for Pond Based Piped Water Supply Scheme using Nandan Bil for Elahabad Mouza. | SM/10288 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 832/BD | 14/07/2023 | 14/07/2023 | Resource Division | 6.2 | 0 | 0 | 0
Total | [13 empty] | 288.88 | 215.39 | 74.56