## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering D | SM/10452 | Retrofitting | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Harirampur Piped Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur. |  | Junior Engineer 2 Sub Division | ORD/000343/2021-2022 | 1922/BSSD | 01/12/2021 | 26/12/2021 | SARKAR CONSTRUCTION (GRP) | 4.84 | 3.65 | 75.48 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering D | SM/10452 | Retrofitting | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 Sub Division | ORD/000111/2022-2023 | 525/BD | 01/04/2022 | 01/05/2022 | ENVIROTECH SOLUTIONS | 3.22 | 3.22 | 100 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering D | SM/10452 | Retrofitting | Providing Functional Household Tap Connection by Retrofitting of present scheme of Harirampur Piped Water Supply Scheme under Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000260/2022-2023 | 3962/BD | 31/03/2023 | 15/05/2023 | SATELLITE CONSTRUCTION | 16.02 | 0 | 0 | 0
Total | [13 empty] | 24.07 | 6.87 | 28.54