## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10455 | Retrofitting | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer Kushmandi | ORD/000328/2021-2022 | 1911/BSSD | 01/12/2021 | 26/12/2021 | KRISHNA PAUL | 4.88 | 4.86 | 99.53 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10455 | Retrofitting | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Preparation of DPR to provide FHTC in connection with Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000115/2022-2023 | 531/BD | 01/04/2022 | 01/05/2022 | ENVIROTECH SOLUTIONS | 2.96 | 2.96 | 100 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte | SM/10455 | Retrofitting | Providing Functional Household Tap Connection by Retrofitting of present scheme of Kushmandi Piped Water Supply Scheme under Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000258/2022-2023 | 3952/BD | 31/03/2023 | 15/05/2023 | M/S. A.D. ENTERPRISE | 17.6 | 0 | 0 | 0
Total | [13 empty] | 25.44 | 7.82 | 30.74