## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10457 | Retrofitting | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Hili Piped Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur. |  | Junior Engineer Hili | ORD/000344/2021-2022 | 1923/BSSD | 01/12/2021 | 26/12/2021 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.81 | 4.48 | 93.22 | 1
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10457 | Retrofitting | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Preparation of DPR to provide FHTC in connection with Augmentation of Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000114/2022-2023 | 530/BD | 01/04/2022 | 01/05/2022 | M/S. SOBHA & CO. | 3.25 | 3.25 | 100 | 1
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Providing Functional House Hold Tap Connection by Retrofitting of parent scheme and Preparation of Augmentation DPR for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | SM/10457 | Retrofitting | Providing Functional House Hold Tap Connection in connection with Retrofitting for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Hili | ORD/000083/2023-2024 | 906/BD | 25/07/2023 | 08/09/2023 | M/S. SARKAR CONSTRUCTION | 22.06 | 0 | 0 | 0
Total | [13 empty] | 30.12 | 7.73 | 25.65