## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 3486/BD | 03/03/2023 | 03/03/2023 | Resource Division | 23.75 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 829/BD | 14/07/2023 | 14/07/2023 | Resource Division | 28.95 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W no. III of Augmentation of Patiram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer-01 | ORD/000248/2023-2024 | 2252/MLMD | 18/07/2023 | 03/01/2026 | M/S PARIMAL DAS. | 12.86 | 11.26 | 87.57 | 70
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Repairing works of Pump House at Head Work Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer Sadar | Junior Engineer HQ 2 | ORD/000192/2022-2023 | 3519/BD | 04/03/2023 | 31/08/2023 | BIPUL SARKAR | 1.1 | 0.13 | 11.61 | 100
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Repairing works of Blower Room at Head Work Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer Sadar | Junior Engineer 2 HQ | ORD/000198/2022-2023 | 3513/BD | 04/03/2023 | 24/03/2023 | AMITAVA MITRA CONTRACTOR & ORDER SUPPLIER | 1.08 | 0.9 | 82.9 | 99
6 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W no. I of Augmentation of Patiram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer-01 | ORD/000021/2023-2024 | 772/MLMD | 26/04/2023 | 10/05/2024 | FUTURE | 13.05 | 10.92 | 83.66 | 100
7 | DAKSHIN DINAJPUR |  | Central Drilling | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 180 Mtrs. Depth) by utilising Departmental Machineries for Patiram W/S Scheme ( T/W- I ) , Balurghat Block under Dakshin Dinajpur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000501/2022-2023 | 1316/CDD | 23/11/2022 | 16/03/2024 | PADMA ENGINEERING & CO. | 14.21 | 12.81 | 90.19 | 100
8 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Payment for the quotation of New Connection of PH NO-III of Patiram PWSS under Patiram CCC in the district of Dakshin Dinajpur |  |  | BILL/00227/2024-2025 | BP-2024-25-99 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 4.03 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Sinking of Tubewell, Laying of Rising Main System, Repairing & Renovation of existing 182 Cum capacity OHR with Construction of Pump House, Blower Room, Construction & Repairing of Boundary Wall, Installation of IEP & Providing FHTC for Part Retrofitting and for Augmentation of Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000259/2022-2023 | 3953/BD | 31/03/2023 | 26/01/2026 | M/S. ANWESHA ENTERPRISE | 242.56 | 11.91 | 4.91 | 25
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Repairing works of Pump House and Latrine at 2nd Tube Well Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer 2 HQ | ORD/000219/2022-2023 | 3818/BD | 23/03/2023 | 19/09/2023 | SUBHRA KANTI GHOSH | 1.4 | 0 | 0 | 100
11 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Patiram Water Supply Scheme in Balurghat Block of Dakshin Dinajpur District. | SM/10471 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Patiram Water Supply Scheme, (Zone- II) in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer-01 | ORD/000023/2023-2024 | 773/MLMD | 26/04/2023 | 30/09/2024 | SOVON KUMAR DAS. | 10.3 | 9.06 | 87.97 | 100
Total | [13 empty] | 353.28 | 56.99 | 16.13