## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of of Uttar Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011659) | Assistant Engineer - I | Junior Engineer-01 | ORD/000260/2023-2024 | 2233/MLMD | 19/07/2023 | 16/11/2023 | DEY ENTERPRISE.. | 13.14 | 9.13 | 69.51 | 69
2 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR UTTAR DAULATPUR W/S SCH (HW), Bansihari Block, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000337/2022-2023 | 1313/CDD | 23/11/2022 | 23/12/2022 | PADMA ENGINEERING & CO. | 15.55 | 12.74 | 81.91 | 1
3 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR UTTAR DAULATPUR W/S SCH (TW-II), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000338/2022-2023 | 1314/CDD | 23/11/2022 | 23/12/2022 | PADMA ENGINEERING & CO. | 15.55 | 11.41 | 73.36 | 1
4 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Uttar Daulatpur,PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000988/2023-2024 | 4003194886 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 3.1 | 3.1 | 100 | 100
5 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Uttar Daulatpur,PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000989/2023-2024 | 4003193495 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 2.77 | 2.77 | 100 | 100
6 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Providing Pipes 250mm dia. and other works for construction of Tube Well for Uttar Daulatpur W/S Scheme (HW) , in Banshihari Block under Dakshin Dinajpur District , Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000523/2022-2023 | 67/CMSD-I(D) | 14/03/2023 | 24/03/2023 | PADMA ENGINEERING & CO. | 0.19 | 0.19 | 100 | 100
7 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 2884/BD | 06/01/2023 | 06/01/2023 | Resource Division | 10.38 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 834/BD | 14/07/2023 | 14/07/2023 | Resource Division | 3.35 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Laying of Rising Main & Providing FHTC, Construction of Pump House, Boundary wall, C.C. Road and Land filling for implementation of Uttar Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sub Division | ORD/000249/2022-2023 | 3946/BD | 31/03/2023 | 30/05/2023 | DURJOY MITRA | 65.44 | 37.57 | 57.41 | 75
10 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Additional Quotation For PH-II Of Uttar Daulatpur w/s Scheme Under Buniadpur CCC |  |  | BILL/03552/2023-2024 | BP-2023-24-556 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 2.72 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Laying distribution pipe line for piped water supply scheme for Uttar Daulatpur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000139/2022-2023 | 2421/BD | 09/11/2022 | 08/01/2023 | ASHOK MITRA | 99.22 | 80.06 | 80.69 | 95
12 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Uttar Daulatpur Piped Water Supply Scheme at Bansihari Block, Under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/11636 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no II of Uttar Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000051/2024-2025 | 3416/MLMD | 23/10/2024 | 21/04/2025 | PABITRA MANDAL | 11.51 | 5.55 | 48.26 | 100
Total | [13 empty] | 242.92 | 162.52 | 66.9