## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Laying distribution pipe line for piped water supply scheme for Baragram PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000138/2022-2023 | 2331/BD | 17/10/2022 | 15/01/2023 | ASHIT KUMAR DEBSHARMA | 182.34 | 177.75 | 97.48 | 1
2 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARAGRAM W/S SCH (TW-II), BANSHIHARI BLOCK DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000256/2022-2023 | 1144/CDD | 07/11/2022 | 07/12/2022 | PADMA ENGINEERING & CO. | 14.08 | 11.81 | 83.91 | 1
3 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 245 Mtrs. Depth) by utilising Departmental Machineries for Baragram W/S Scheme (HW ) , Banshihari Block under Dakshin Dinajpur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000500/2022-2023 | 1143/CDD | 07/11/2022 | 01/03/2024 | PADMA ENGINEERING & CO. | 14.08 | 11.94 | 84.82 | 100
4 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 2562/BD | 06/12/2022 | 06/12/2022 | Resource Division | 18.28 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Laying of Rising Main , Providing FHTC, Construction of 200 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House for implementation of Baragram Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000004/2023-2024 | 49/BD | 10/04/2023 | 21/03/2026 | BRISTI CONSTRUCTION | 172.1 | 17.89 | 10.39 | 15
6 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Supply, installation, commissioning and trial run of electro-mechanical components of BARAGRAM Water Supply Scheme T/W no. I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011705) | Assistant Engineer - I | Junior Engineer-01 | ORD/000232/2023-2024 | 2251/MLMD | 18/07/2023 | 16/10/2023 | R.N.S. TRADING. | 11.94 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Making compound lighting arrangement with allied works at T/W no. I of Baragram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011705) | Assistant Engineer - I | Junior Engineer-01 | ORD/000601/2023-2024 | 2648/MLMD | 10/08/2023 | 24/09/2023 | M/S. MAYUKH BHADURI | 3.86 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Supply, installation, commissioning and trial run of electro-mechanical components of BARAGRAM Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001100/2022-2023 | 417/MLMD | 14/03/2023 | 20/09/2024 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 11.96 | 10.23 | 85.54 | 96
9 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 2889/BD | 06/01/2023 | 06/01/2023 | Resource Division | 34.83 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 3446/BD | 01/03/2023 | 01/03/2023 | Resource Division | 0.69 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Baragram Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000161/2024-2025 | 2234/BD | 12/11/2024 | 23/08/2025 | SARADA ENTERPRISE | 26.22 | 0 | 0 | 95
12 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 17/10/2024 | RANJAN SARKAR | 5.25 | 0 | 0 | 100
13 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 254/BD | 21/02/2024 | 21/02/2024 | Resource Division | 8.55 | 0 | 0 | 0
14 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Laying distribution pipe line for piped water supply scheme for Baragram PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | BILL/00185/2024-2025 | BP-2024-25-118 | 04/09/2024 | 04/09/2024 | ASHIT KUMAR DEBSHARMA | 9.43 | 0 | 0 | 0
15 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Baragram, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02475/2023-2024 | BP-2023-24-405 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 6.72 | 0 | 0 | 0
16 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Baragram PWSS in Banshihari Block in Dakshin Dinajpur | SM/11670 | New | Quotation Payment for Pump House No I of Baragram PWSS under Buniadpur CCC. |  |  | BILL/03501/2023-2024 | BP-2023-24-521 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 4.35 | 0 | 0 | 0
Total | [13 empty] | 524.67 | 229.62 | 43.76