## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Bhoir W/S Scheme (TW-II), Banshihari block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000470/2022-2023 | 306/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 10.33 | 8.23 | 79.65 | 100
2 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BHOIR W/S SCH (HW), BANSHIHARI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000271/2022-2023 | 1145/CDD | 07/11/2022 | 07/12/2022 | PADMA ENGINEERING & CO. | 14.08 | 9.58 | 68.03 | 1
3 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Laying of Rising Main, Partial Distribution of pipeline, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including Soil Investigation, Construction of Pump House for implementation of Bhoir Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000201/2022-2023 | 3507/BD | 04/03/2023 | 17/12/2025 | M/S. ANWESHA ENTERPRISE | 406.64 | 241.36 | 59.35 | 45
4 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bhoir Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011765) | Assistant Engineer - I | Junior Engineer-01 | ORD/001125/2022-2023 | 508/MLMD | 20/03/2023 | 16/09/2023 | DAS CONSTRUCTION | 25.78 | 22.67 | 87.92 | 70
5 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhoir PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000437/2023-2024 | 4003196923 | 21/07/2023 | 19/10/2023 | W.B.S.E.D.C.LTD | 5.6 | 5.6 | 100 | 100
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 2894/BD | 06/01/2023 | 06/01/2023 | Resource Division | 13.65 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Hiring of Diesel Driven Motor Cab (BS-IV & Above) hiving contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000210/2023-2024 | 12/S&WSD | 15/01/2024 | 31/07/2024 | SULEKHA GHOSH | 0.94 | 1.41 | 149.44 | 15
8 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Laying of balance Distribution pipe line and Construction of Boundary Wall and allied works at Bhoir Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000147/2024-2025 | 2053/BD | 03/10/2024 | 01/04/2025 | THE NEW LOKNATH CONSTRUCTION | 236.45 | 44.02 | 18.62 | 85
9 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 17/10/2024 | RANJAN SARKAR | 5.25 | 0 | 0 | 100
10 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 247/BD | 21/02/2024 | 21/02/2024 | Resource Division | 13.02 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bhoir PWSS , Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02467/2023-2024 | BP-2023-24-395 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 10.48 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | Bhoir pipe water supply scheme in Banshihari Block under Balurghat Division P.H.E. Dte. in the district of Dakshin Dinajpur District. | SM/11851 | New | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Patun more to Jordighi Road via Badalpur from (chainage 9.00 K.M to 11.90 K.M). |  |  | BILL/00012/2025-2026 |  | 22/04/2025 | 22/04/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 6.18 | 0 | 0 | 0
Total | [13 empty] | 748.4 | 332.85 | 44.48