## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer-01 | ORD/000197/2023-2024 | 2133/MLMD | 07/07/2023 | 03/10/2028 | KARMAKAR CONSTRICTION. | 6.97 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer-01 | ORD/000228/2023-2024 | 2248/MLMD | 18/07/2023 | 16/10/2023 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.07 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer-01 | ORD/000229/2023-2024 | 2249/MLMD | 18/07/2023 | 16/10/2023 | JOY MAA SANTOSHI ENTERPRISE. | 8.06 | 0 | 0 | 85
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Providing FHTC by retrofitting of parent scheme of Daultapur Piped Water Supply Scheme under Banshihari & Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000257/2022-2023 | 3950/BD | 31/03/2023 | 15/05/2023 | R.P. CHOUDHURY CONSTRUCTION. | 12.1 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 3494/BD | 03/03/2023 | 03/03/2023 | Resource Division | 29.32 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Laying of Rising Main, Providing FHTC, Construction of 150 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House repairing, Construction of Boundary Wall for Augmentation of DAULATPUR Piped Water Supply Scheme at Banshihari and Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000248/2022-2023 | 3945/BD | 31/03/2023 | 01/07/2025 | DURJOY MITRA | 188.44 | 0 | 0 | 38
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Erection of Permanent Type village wise Scheme Information Board at different Piped Water Supply Schemes under JJM as per departmental design and drawing for Gangarampur, Banshihari, Harirampur & Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000189/2023-2024 | 2070/BD | 16/12/2023 | 30/01/2024 | M.A. ENTERPRISE | 10.09 | 0 | 0 | 91
8 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. III in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer-01 | ORD/000230/2023-2024 | 2250/MLMD | 18/07/2023 | 16/10/2023 | JIBON GHOSH. | 8.07 | 0 | 0 | 100
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 2 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 09/01/2024 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 0 | 100
10 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 253/BD | 21/02/2024 | 21/02/2024 | Resource Division | 10.71 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Daulatpur Piped Water Supply Scheme | SM/11852 | Augmentation | Laying distribution pipe line for augmentation of Daulatpur Pipe Water Supply Scheme at Banshihari & Harirampur Dev. Block in the district of Dakhin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000144/2022-2023 | 2433/BD | 11/11/2022 | 10/01/2023 | DIPESH BHOWMIK | 170.15 | 0 | 0 | 100
Total | [13 empty] | 476.26 | 0 | 0