## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUNDAIL W/S SCH TW-II, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000359/2022-2023 | 1169/CDD | 09/11/2022 | 09/12/2022 | M/S SAIKAT ENTERPRISE | 8.28 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUNDAIL W/S SCH TW-I, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000361/2022-2023 | 1168/CDD | 09/11/2022 | 09/12/2022 | S B S ENTERPRISE | 8.2 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SUNDAIL, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000268/2023-2024 | 4003195607 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 6.61 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SUNDAIL, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000269/2023-2024 | 4003195612 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 6.85 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Additional carraige of gravels for Construction of Tube well at SUNDAIL PWSS TW-II, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. |  |  | ORD/000478/2022-2023 | 586/CMSD-I(D) | 30/11/2022 | 07/12/2022 | M/S SAIKAT ENTERPRISE | 0.59 | 0 | 0 | 100
6 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Additional carraige of gravels for Construction of Tube well at SUNDAIL PWSS TW-I, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. |  |  | ORD/000480/2022-2023 | 585/CMSD-I(D) | 30/11/2022 | 07/12/2022 | S B S ENTERPRISE | 0.59 | 0 | 0 | 100
7 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2883/BD | 06/01/2023 | 06/01/2023 | Resource Division | 11.06 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 836/BD | 14/07/2023 | 14/07/2023 | Resource Division | 7.34 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Laying of Rising Main, Providing FHTC, Construction of 200 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Sundail Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000012/2023-2024 | 189/BD | 28/04/2023 | 15/04/2026 | M/S. ANWESHA ENTERPRISE | 163.05 | 0 | 0 | 36
10 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 2 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 09/01/2024 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 0 | 100
11 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | SUNDAIL PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11929 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sundail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011985) | Assistant Engineer - I | Junior Engineer-01 | ORD/000178/2023-2024 | 2097/MLMD | 04/07/2023 | 26/02/2026 | GHOSH BROTHERS... | 26.29 | 0 | 0 | 90
Total | [13 empty] | 260.17 | 0 | 0