## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Laying distribution pipe line for piped water supply scheme at BRAHMANGRAM under Ground Water Based Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000174/2022-2023 | 3292/BD | 09/02/2023 | 10/05/2023 | BOSE CONSTRUCTION | 329.6 | 261.21 | 79.25 | 82
2 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Providing drilling crew & other allied works for construction of TW (250mm x 150mm x 120mtr. depth) by utilising Departmental machineries for Brahmangaon WS Scheme (TW-II), harirampur Block under Dakshin Dinajpur District, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000336/2022-2023 | 1397/CDD | 28/11/2022 | 28/12/2022 | CHANDA ENTERPRISE | 8.26 | 6.32 | 76.52 | 1
3 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BRAHMANGAON W/S SCH TW-I, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000358/2022-2023 | 1170/CDD | 09/11/2022 | 09/12/2022 | M/S S.K.GHOSH & CO. | 8.28 | 6.67 | 80.56 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000286/2023-2024 | 4003193779 | 15/07/2023 | 13/10/2023 | W.B.S.E.D.C.LTD | 4.85 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000305/2023-2024 | 4003193779 | 15/07/2023 | 13/10/2023 | W.B.S.E.D.C.LTD | 4.85 | 4.85 | 100 | 100
6 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000287/2023-2024 | 4003193767 | 15/07/2023 | 13/10/2023 | W.B.S.E.D.C.LTD | 3.03 | 3.03 | 100 | 100
7 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Additional carraige of gravels for Construction of Tube well at BRAHMANGAON PWSS TW-II, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. |  |  | ORD/000479/2022-2023 | 588/CMSD-I(D) | 30/11/2022 | 07/12/2022 | M/S S.K.GHOSH & CO. | 0.59 | 0.43 | 71.8 | 100
8 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Additional carraige of gravels for Construction of Tube well at BRAHMANGAON PWSS , Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. |  |  | ORD/000481/2022-2023 | 587/CMSD-I(D) | 30/11/2022 | 07/12/2022 | CHANDA ENTERPRISE | 0.59 | 0.42 | 71.55 | 100
9 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 2875/BD | 06/01/2023 | 06/01/2023 | Resource Division | 10.16 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 248/BD | 21/02/2024 | 21/02/2024 | Resource Division | 16.65 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Brahmangaon Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011983) | Assistant Engineer - I | Junior Engineer-01 | ORD/000016/2023-2024 | 779/MLMD | 27/04/2023 | 25/06/2026 | ANIMA ENTERPRISE | 26.58 | 18.97 | 71.37 | 65
12 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Laying of Rising Main, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Brahmangaon Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000018/2023-2024 | 202/BD | 28/04/2023 | 30/05/2026 | DURJOY MITRA | 215.09 | 73.92 | 34.37 | 80
13 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BRAHMANGAON PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte. | SM/11930 | New | Laying of additional distribution pipeline for the left out area, construction of approach road and other allied works within command area of Brahmangaon Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000165/2024-2025 | 2230/BD | 12/11/2024 | 08/09/2025 | MATIUR RAHAMAN | 51.46 | 0 | 0 | 60
Total | [13 empty] | 679.99 | 375.82 | 55.27